## Slide 1
Risk ID | Risk | Risk Description | Inherent Risk Score |  |  | Risk Owner | Controls | Residual Risk Score |  |  | Further Actions / Notes | Target Risk
 |  |  | P | I | RS |  |  | P | I | RS |  | 
FSR0015 | IS infrastructure | The IS infrastructure across the organisation is being carefully observed as a result of a number of system failures over recent months. Outages and service disruption have become more frequent for CM end users over the past 3 months. A full record of all issues are logged and kept up-to-date. On occasions, technology failure has resulted in business continuity plans being stood up in order to continue to provide service delivery to our communities and victims of crime. The longest outage was 36 hours with no command and control or incoming calls via SAFE (81 service requests at present with 10 identified as major since March 2022). The recent CM technological innovations have supported the BCP in respect of live chat, call-backs and SOH. However, the frequency of failures in technology, including SAFE command and control, SKYPE incoming calls, CISCO and Airwave, appear far in excess of other forces using the same technological platforms as us, and potentially highlight infrastructure deficiencies of which must be resolved in order for us to effectively service incoming demand. | 4 | 4 | 16 | DCC Cooper | . Corporate Services have placed additional resource in to fully understand the issues and support a long term strategic remedy. CM and enablers are working closely with service providers including SAAB, SJS and BT. The recent CM technological innovations have supported the BCP in respect of live chat, call-backs and SOH. Scoping document for technical infrastructure review has been prepared and will be circulated with SAAB. The risk is reported to the Strategic Risk meeting. The risk is reported to FEB and to JIAC. Chief Supt – Corporate Services chairs regular ‘Technical Infrastructure Review’ meetings | 4 | 3 | 12 | Once the final report is submitted by the part-taking outside agencies, it will be circulated along with recommendations on what is needed to be done. | 
*Risk scores: P = Probability, I = Impact, RS = Risk Score
Nottinghamshire Police Strategic Risk Register

## Slide 2
Risk ID | Risk | Risk Description | Inherent Risk Score |  |  | Risk Owner | Controls | Residual Risk Score |  |  | Further Actions / Notes | Target Risk
 |  |  | P | I | RS |  |  | P | I | RS |  | 
FSR0017 | Having an insufficient number of qualified detectives. Specific issue in Major Crime. | The recruitment and retention of the appropriate number of detectives is a national issue for all forces which could result in inexperienced officers investigating serious crimes. It could also lead to significant pressure for those existing detectives and an inadequate level of service for victims of crime. This is a specific issue for Major Crime. | 4 | 3 | 12 | ACC Griffin | Candidates sought from local universities for the graduate investigator scheme. Fast track to DC. Major Crime have brought in a PiP3 member of staff from the region to oversee one of the more difficult cases. Mentor in place to provide support and guidance for new staff. Recruitment plan for officers in 23/24 specifically focuses on Detective recruitment programmes. Police Pass purchased to assist in NIE examination rates increasing. TVP utilised to support retention in critical roles. Op Consolidation utilised (x5) to increase officer knowledge and awareness of PIP roles. | 3 | 2 | 6 | The risk will be reported to the Strategic Risk meeting. The risk will continue to be reported to FEB and to JIAC. Training courses planned for the new DS’ and plans to upskill them in the next 6 months. | 4

## Slide 3
Risk ID | Risk | Risk Description | Inherent Risk Score |  |  | Risk Owner | Controls | Residual Risk Score |  |  | Further Actions / Notes | Target Risk
 |  |  | P | I | RS |  |  | P | I | RS |  | 
FSR0010 | Loss of confidence and trust by communities in Nottinghamshire due to the murders of women in public open spaces nationally and other high profile issues resulting to police officer misconduct. | The murders of women in public open spaces nationally, including an offence perpetrated by a serving Police Officer, have contributed to a loss of confidence in the police service and heightened fear amongst women and some communities in Nottinghamshire. These feelings have been compounded by further breaches of trust and professional standards by serving officers across UK policing, many of which are highlighted in the Baroness Casey Review. | 3 | 4 | 12 | DCC Cooper | Training package encouraging officers and staff to take action and identify behaviour that is concerning. Implementation of Government’s Violence against Women and Girls Strategy and Action Plan. Community engagement. Referrals into PSD. The risk is reported to the Strategic Risk meeting. The risk is reported to FEB and to JIAC. We are following the latest NPCC/CoP guidance in relation to the further vetting of staff. Call it Out campaign. Police Race Action Plan Gold group chaired by the DCC. | 2 | 3 | 6 | Scoping of resources required to achieve what the Met are doing in relation to running all current employees through the PNC. | 4

## Slide 4
Risk ID | Risk | Risk Description | Inherent Risk Score |  |  | Risk Owner | Controls | Residual Risk Score |  |  | Further Actions / Notes | Target Risk
 |  |  | P | I | RS |  |  | P | I | RS |  | 
FSR0009 | Inability to demonstrate the timely completion and sign off, of public accounts. | 2020-21 accounts have not yet been subject to audit. The draft 2021/22 accounts have not yet been reviewed in line with the statutory deadline (30/09/20220). These are likely to be available by the end of the calendar year. The impact of this is that the force is unable to demonstrate accountability to its stakeholders in line with statutory requirements. This could result in reputational damage to the organisation. | 4 | 3 | 12 | Mark Kimberley | Monthly updates into FEB. Quarterly reporting into JIAC. COT/CFO oversight. Increased number of resources in the Finance Department associated with the production of the final accounts. | 3 | 3 | 9 | The risk will be reported to the Strategic Risk meeting. The risk will be reported to FEB and to JIAC. Accounts completed and audit 2021 started in May 2022. Lack of external audit resources means this is unlikely to be completed by the end of the financial year. Audit of the 2021/22 accounts is unlikely to start until 2023/24. 09.01.23 – Reassurance given by CFO that controls/mitigation in place to facilitate audits. | 8
March 2023

## Slide 5
Risk ID | Risk | Risk Description | Inherent Risk Score |  |  | Risk Owner | Controls | Residual Risk Score |  |  | Further Actions / Notes | Target Risk
 |  |  | P | I | RS |  |  | P | I | RS |  | 
FSR0006 | Having high numbers of inexperienced officers as a result of Op Uplift due to their short length of service. | The recruitment of a large number of new officers into the force through Operation Uplift could result in a high level of inexperienced, young in service officers. This could add extra pressure and additional workloads for existing officers whilst these new officers work through their training. | 4 | 3 | 12 | ACC Hooks | Negotiated release of Response Officers through Tactical Workforce Planning. The Chief Constable has agreed a new attachments process for all recruits at their week 90. They will have a mandatory six month attachment within investigations or neighbourhoods. Additional inspectors and sergeants were added in to support in line management Training days to include areas for improvement identified through Command/Learning and Development | 3 | 2 | 6 | The risk will be reported to the Strategic Risk meeting. The risk will be reported to FEB and to JIAC. 09.01.23 ACC Hooks confirmed Response/Demand Review initiated. Head People Services added force reviewing option of ‘Rejoiner’ scheme. | 4

## Slide 6
Risk ID | Risk | Risk Description | Inherent Risk Score |  |  | Risk Owner | Controls | Residual Risk Score |  |  | Further Actions / Notes | Target Risk
 |  |  | P | I | RS |  |  | P | I | RS |  | 
FSR0007 | No GIRR accreditation resulting in risk to the organisation’s information security, increased exposure to cyber attacks and reputational damage. This is intensified by the lack of Information Management Lead and Data Protection Officer, which could lead to non compliance with statutory and regulatory requirements. | Due to a lack of Governance and Information Risk Return (GIRR) accreditation, there is an increased risk that corporate information will be compromised resulting in monetary penalties and reputational damage. | 4 | 3 | 12 | DCC Cooper | Plans prepared to renew Force accreditation by July 2022. Continued liaison with NPIRMT. Force will work to an annual cycle of compliance moving forward for the variety of frameworks it is required to comply with. Fast track recruitment into the Information Management Lead and Data Protection Officer post on a 6 month secondment (closing date for expressions of interest 13th May 2022). Assistance from neighbouring forces Derbyshire and Northants. | 3 | 2 | 6 | The risk will be reported to the Strategic Risk meeting. The risk will be reported to FEB and to JIAC. The risk will be reported to the Strategic Risk meeting and managed through the Information Management Board. Active consideration of permanent recruitment to the role. Chief Supt Lawton, Corporate Services has oversight of this area. We now do the SyAP and we will be sent our maturity ratings report on 17.05.2023, which will inform our next steps. | 4

## Slide 7
Risk ID | Risk | Risk Description | Inherent Risk Score |  |  | Risk Owner | Controls | Residual Risk Score |  |  | Further Actions / Notes | Target Risk
 |  |  | P | I | RS |  |  | P | I | RS |  | 
FSR0012 | Failure to meet the environmental targets proposed under the Environmental Act 2021. | There is a clear governmental directive to improve our environmental efficiency. The speed of change, along with increase in costs and demand, may make this net zero target hard to achieve, thereby potentially effecting the environment, finances and ability to operate . | 3 | 2 | 6 | DCC Cooper | Solar panelling on police premises. Investment in new buildings, which are more energy efficient and less carbon impairing. Reduction in the size of our estate. Integrated working such as with the Fore Service and the Council. Risk appetite for this area is accepted given the Govt. targets are many years away. The risk is reported to the Strategic Risk meeting. The risk is reported to FEB and to JIAC. | 2 | 2 | 4 | This risk has a ‘negative outlook.’ The Carbon trust are coming in to force to review our work in this area via the Estates Department. This review will generate an action plan for the Force to work to. Chris Ackroyd is working on the decarbonisation of the fleet. | 4

## Slide 8
Risk ID | Risk | Risk Description | Inherent Risk Score |  |  | Risk Owner | Controls | Residual Risk Score |  |  | Further Actions / Notes | Target Risk
 |  |  | P | I | RS |  |  | P | I | RS |  | 
FSR0008 | Loss of public trust and confidence and reputational damage as a result of data quality issues and crime data integrity. | The HMICFRS Integrated PEEL Inspection 2020/21 report graded the Force’s crime data integrity - ‘requires improvement.’ This suggested the force was under-reporting potential crimes. This could lead to a loss of trust and confidence and victims not receiving a full service. | 3 | 2 | 6 | DCC Cooper | Regular audits introduced for key crime types to ensure that effective governance is in place. Outcomes of audits to be fed into Data Quality Board and appropriate remedial action taken to address any emerging issues. Oversight of progress on the PEEL AFIs by the DCC. | 2 | 2 | 4 | The risk will be reported to the Strategic Risk meeting and Integrity Board and managed through the Crime Data Integrity Board. The risk will be reported to FEB and to JIAC. 9.1.23 – DCC Cooper confirmed Force working with Humberside in relation to Peer Review. | 2