## Slide 1
Risk ID | Risk | Risk Description | Inherent Risk Score |  |  | Risk Owner | Controls | Residual Risk Score |  |  | Further Actions / Notes | Target Risk
 |  |  | P | I | RS |  |  | P | I | RS |  | 
FSR00 15 | IS infrastructure | The IS infrastructure across the organisation is being carefully observed as a result of a number of system failures over recent months. Outages and service disruption have become more frequent for CM end users over the past 3 months. A full record of all issues are logged and kept up-to-date. On occasions, technology failure has resulted in business continuity plans being stood up in order to continue to provide service delivery to our communities and victims of crime. The recent CM technological innovations have supported the BCP in respect of live chat, call-backs and SOH. However, the frequency of failures in technology, appear far in excess of other forces using the same technological platforms as us, and potentially highlight infrastructure deficiencies of which must be resolved in order for us to effectively service incoming demand. | 4 | 4 | 16 | DCC Cooper | . Corporate Services have placed additional resource in to fully understand the issues and support a long term strategic remedy. CM and enablers are working closely with service providers. The recent CM technological innovations have supported the BCP in respect of live chat, call-backs and SOH. Scoping document for technical infrastructure review has been prepared. | 4 | 3 | 12 | The risk will be reported to the Strategic Risk meeting. The risk will be reported to FEB and to JIAC. Chief Supt – Corporate Services will chair regular ‘Technical Infrastructure Review’ meetings. | 
*Risk scores: P = Probability, I = Impact, RS = Risk Score
Nottinghamshire Police Strategic Risk Register

## Slide 2
Risk ID | Risk | Risk Description | Inherent Risk Score |  |  | Risk Owner | Controls | Residual Risk Score |  |  | Further Actions / Notes | Target Risk
 |  |  | P | I | RS |  |  | P | I | RS |  | 
FSR0017 | Having an insufficient number of qualified detectives. | The recruitment and retention of the appropriate number of detectives is a national issue for all forces which could result in inexperienced officers investigating serious crimes. It could also lead to significant pressure for those existing detectives and an inadequate level of service for victims of crime. | 4 | 3 | 12 | ACC Griffin | Candidates sought from local universities for the graduate investigator scheme. Fast track to DC. Report to FEB with options for COT decision will be prepared. | 3 | 2 | 6 | The risk will be reported to the Strategic Risk meeting. The risk will continue to be reported to FEB and to JIAC. | 4
FSR0010 | Loss of confidence and trust by communities in Nottinghamshire due to the murders of women in public open spaces nationally and other high profile issues resulting to police officer misconduct. | The murders of women in public open spaces nationally, including an offence perpetrated by a serving Police Officer, have contributed to a loss of confidence in the police service and heightened fear amongst women and some communities in Nottinghamshire. These feelings have been compounded by further breaches of trust and professional standards by serving officers across UK policing. | 3 | 4 | 12 | DCC Cooper | Training package encouraging officers and staff to take action and identify behaviour that is concerning. Implementation of Government’s Violence against Women and Girls Strategy and Action Plan. Community engagement. Referrals into PSD. | 2 | 3 | 6 | The risk will be reported to the Strategic Risk meeting. The risk will be reported to FEB and to JIAC. Latest NPCC/CoP guidance in relation to the further vetting of staff. | 4

## Slide 3
Risk ID | Risk | Risk Description | Inherent Risk Score |  |  | Risk Owner | Controls | Residual Risk Score |  |  | Further Actions / Notes | Target Risk
 |  |  | P | I | RS |  |  | P | I | RS |  | 
FSR0009 | Inability to demonstrate the timely completion and sign off, of public accounts. | 2020-21 accounts have not yet been subject to audit. The draft 2021/22 accounts have not yet been reviewed in line with the statutory deadline (30/09/20220). These are likely to be available by the end of the calendar year. The impact of this is that the force is unable to demonstrate accountability to its stakeholders in line with statutory requirements. This could result in reputational damage to the organisation. | 4 | 3 | 12 | Mark Kimberley | Monthly updates into FEB. Quarterly reporting into JIAC. COT/CFO oversight. Increased number of resources in the Finance Department associated with the production of the final accounts. | 3 | 3 | 9 | The risk will be reported to the Strategic Risk meeting. The risk will be reported to FEB and to JIAC. Accounts completed and audit 2021 started in May 2022. Lack of external audit resources means this is unlikely to be completed by the end of the financial year. Audit of the 2021/22 accounts is unlikely to start until 2023/24. 09.01.23 – Reassurance given by CFO that controls/mitigation in place to facilitate audits. | 8

## Slide 4
Risk ID | Risk | Risk Description | Inherent Risk Score |  |  | Risk Owner | Controls | Residual Risk Score |  |  | Further Actions / Notes | Target Risk
 |  |  | P | I | RS |  |  | P | I | RS |  | 
FSR0006 | Having high numbers of inexperienced officers as a result of Op Uplift due to their short length of service. | The recruitment of a large number of new officers into the force through Operation Uplift could result in a high level of inexperienced, young in service officers. This could add extra pressure and additional workloads for existing officers whilst these new officers work through their training. | 4 | 3 | 12 | ACC Hooks | Negotiated release of Response Officers through Tactical Workforce Planning. | 3 | 2 | 6 | The risk will be reported to the Strategic Risk meeting. The risk will be reported to FEB and to JIAC. 09.01.23 ACC Hooks confirmed Response/Demand Review initiated. Head People Services added force reviewing option of ‘Rejoiner’ scheme. | 4

## Slide 5
Risk ID | Risk | Risk Description | Inherent Risk Score |  |  | Risk Owner | Controls | Residual Risk Score |  |  | Further Actions / Notes | Target Risk
 |  |  | P | I | RS |  |  | P | I | RS |  | 
FSR0007 | No GIRR accreditation resulting in risk to the organisation’s information security, increased exposure to cyber attacks and reputational damage. This is intensified by the lack of Information Management Lead and Data Protection Officer, which could lead to non compliance with statutory and regulatory requirements. | Due to a lack of Governance and Information Risk Return (GIRR) accreditation, there is an increased risk that corporate information will be compromised resulting in monetary penalties and reputational damage. | 4 | 3 | 12 | DCC Cooper | Plans prepared to renew Force accreditation by July 2022. Continued liaison with NPIRMT. Force will work to an annual cycle of compliance moving forward for the variety of frameworks it is required to comply with. Fast track recruitment into the Information Management Lead and Data Protection Officer post on a 6 month secondment (closing date for expressions of interest 13th May 2022). Assistance from neighbouring forces Derbyshire and Northants. | 3 | 2 | 6 | The risk will be reported to the Strategic Risk meeting. The risk will be reported to FEB and to JIAC. The risk will be reported to the Strategic Risk meeting and managed through the Information Management Board. Active consideration of permanent recruitment to the role. Chief Supt Corporate Services has oversight of this area. 9.1.23 – Chief Supt confirmed force chosen as pilot for SIAB. | 4

## Slide 6
Risk ID | Risk | Risk Description | Inherent Risk Score |  |  | Risk Owner | Controls | Residual Risk Score |  |  | Further Actions / Notes | Target Risk
 |  |  | P | I | RS |  |  | P | I | RS |  | 
FS0016 | Data assurance in respect of covert material. | Report and inspection from IPCO regarding the management, including retention and deletion, of covert material. Nottinghamshire Police need a local policy and data pathways for all products, that are IPCO compliant, even where this deviates from NPCC guidance. This risk is holding personal information where no necessity exists or is in excess of the minimum necessary period. A progress update is required by March 2023. | 3 | 3 | 9 | DCC Cooper | An action plan is in place to address the identified gaps from the inspection, however as these are not complete the risk remains the same. Progress is tracked through governance meetings and, as actions are completed, the risk score will be re-assessed. Covert pathways mapped. Covert material held in Force Intelligence, CAB, SOC, SHU has been scheduled to enable management of RRD. Covert policies being finalised to agree RRD timescales. Completion expected 10.02.2023. Briefing sessions to staff requesting and handling covert material is being arranged for February. | 3 | 2 | 6 |  | 

## Slide 7
Risk ID | Risk | Risk Description | Inherent Risk Score |  |  | Risk Owner | Controls | Residual Risk Score |  |  | Further Actions / Notes | Target Risk
 |  |  | P | I | RS |  |  | P | I | RS |  | 
FSR0013 | Supply chain issues for vital equipment – specifically laptops and vehicles in force. | Due to supply chain issues, including a lack of computer chips, vehicle parts and other bespoke products the force may not be able to supply laptops to new officers. It may also restrict access to force vehicles which are held up on the production line. | 3 | 3 | 9 | DCC Cooper | Re-distribution of laptops according to role. Early ordering of vehicles and adaption of retention plan. Stock piling where available. Further negotiation of contracts through procurement. | 3 | 2 | 6 | The risk will be reported to the Strategic Risk meeting. The risk will be reported to FEB and to JIAC. 9.1.23 – DCC Cooper confirmed supply issues mostly mitigated but some international issue remain. | 4
FSR0005 | Lack of an appropriate procurement process in place to manage existing and future contracts. | The transfer of Procurement services from MINT back in force, to be managed locally, could result in a decline in service levels. There could also be a delay in contracts being issued or re-negotiated, whilst staff work through the transfer of knowledge and establish the section within force. This is coupled with current challenges around recruitment to roles and retention of staff. | 3 | 3 | 9 | Danny Baker, Head of Finance | Prioritisation of contractual work through the Procurement Prioritisation meeting. Recruitment to fill key vacancies. Regular meetings with COT. Force wide communications regarding changes and activity. | 2 | 2 | 4 | The risk will be reported to the Strategic Risk meeting. The risk will be reported to FEB and to JIAC. As the transition progresses, force wide communications will continue to update staff. 9.1.23 – Risk allocated to Head of Finance who is working with Blue Light Commercial to mitigate. | 4

## Slide 8
Risk ID | Risk | Risk Description | Inherent Risk Score |  |  | Risk Owner | Controls | Residual Risk Score |  |  | Further Actions / Notes | Target Risk
 |  |  | P | I | RS |  |  | P | I | RS |  | 
FSR0011 | Loss of staff and failure to recruit into police staff posts due to the cost of living crisis. | The cost of living crisis and rise in household costs may result in employees struggling financially and feeling under valued. This may present itself in the wellbeing of staff and an increase in sickness rates across the force in addition to greater disparity between pay levels. | 3 | 3 | 9 | DCC Cooper | Wellbeing initiatives focussing on financial support and mental health. Monitor through Career Conversations. Link with Benevolent Fund. Please also refer to the Operation Uplift risk. Reduction of public sector competitiveness renumeration. EDI plan. Integrity messenger. PROUD/Code of Ethics. | 2 | 3 | 6 | The risk will be reported to the Strategic Risk meeting. The risk will be reported to FEB and to JIAC. | 2
FSR0012 | Failure to meet the environmental targets proposed under the Environmental Act 2021. | There is a clear governmental directive to improve our environmental efficiency. The speed of change, along with increase in costs and demand, may make this net zero target hard to achieve, thereby potentially effecting the environment, finances and ability to operate . | 3 | 2 | 6 | DCC Cooper | Solar panelling on police premises. Investment in new buildings, which are more energy efficient and less carbon impairing. Reduction in the size of our estate. Integrated working such as with the Fore Service and the Council. Risk appetite for this area is accepted given the Govt. targets are many years away. | 2 | 2 | 4 | The risk will be reported to the Strategic Risk meeting. The risk will be reported to FEB and to JIAC. This risk has a ‘negative outlook.’ | 4

## Slide 9
Risk ID | Risk | Risk Description | Inherent Risk Score |  |  | Risk Owner | Controls | Residual Risk Score |  |  | Further Actions / Notes | Target Risk
 |  |  | P | I | RS |  |  | P | I | RS |  | 
FSR0008 | Loss of public trust and confidence and reputational damage as a result of data quality issues and crime data integrity. | The HMICFRS Integrated PEEL Inspection 2020/21 report graded the Force’s crime data integrity - ‘requires improvement.’ This suggested the force was under-reporting potential crimes. This could lead to a loss of trust and confidence and victims not receiving a full service. | 3 | 2 | 6 | DCC Cooper | Regular audits introduced for key crime types to ensure that effective governance is in place. Outcomes of audits to be fed into Data Quality Board and appropriate remedial action taken to address any emerging issues. Oversight of progress on the PEEL AFIs by the DCC. | 2 | 2 | 4 | The risk will be reported to the Strategic Risk meeting and Integrity Board and managed through the Crime Data Integrity Board. The risk will be reported to FEB and to JIAC. 9.1.23 – DCC Cooper confirmed Force working with Humberside in relation to Peer Review. | 2