| For Information |  |
| --- | --- |
| Public/Non-Public* | Public |
| Report to: | - Joint Audit and Scrutiny Panel |
| Date of Meeting: | 29th April 2022 |
| Report of: | DCC Barber |
| Report Author: | Amanda Froggatt, Corporate Development Manager |
| E-mail: | amanda.froggatt@nottinghamshire.pnn.police.uk |
| Other Contacts: | Laura Spinks, Force Assurance Lead |
| Agenda Item: | 4 |

- Strategic Risk Management Report Nottinghamshire Police and Nottinghamshire Police and Crime Commissioner

- Purpose of the Report

  - The purpose of this report is to provide the Joint Audit and Scrutiny Panel (JASP) with an up-to-date picture of strategic risk management across the Force and the Office of the Police and Crime Commissioner (OPCC).

- Recommendations

  - It is recommended that JASP notes the current approach to strategic risk management and considers the assurance that this report provides as to the effectiveness of those arrangements within the Force and OPCC.

  - It is recommended that JASP notes the one very high risk on the Force’s strategic risk register, namely Multi-Force Shared Service (MFSS) transfer of payroll system to the new Fusion solution.

2.3	It is recommended that JASP notes the accompanying appendix (Appendix 2), which outlines more in-depth explanations of the mitigation in place in relation to the Force’s high-level strategic risk.

- Reasons for Recommendations

  - A Strategic Risk Report is provided to the JASP on a quarterly basis to keep the Board informed as to the level of strategic risk within the Force and OPCC and provide assurance as to the effectiveness of risk management arrangements.

- Summary of Key Points

4.1	At the Force Executive Board in November 2021, it was agreed that five risks would be removed from the Force’s Strategic Risk Register due to the rationale presented to the Board. These risks were either closed or moved to be managed at Departmental level.

4.3	No new Force strategic risks have been identified for tis reporting period.

4.4	Appendix 2 provides the detail of the mitigation in place for the Force’s current strategic risk.

4.5	With the introduction of JCAD, the Force’s Risk Management tool, in 2020 the organisation has an opportunity to strengthen its governance and assurance processes for risk management. The tool enables departmental heads to have oversight of all risks across the force, so they can identify common themes and interdependencies.

4.6	The Mazars audit conducted in 2021 found that the Force has limited assurance in relation to its current risk management approach. As a result, Corporate Development are undertaking a review of Risk Management processes and will provide options on the way forward to the Senior Management Team. All, of the Force Risk Management documentation is also being reviewed during this process.

4.7	The Force and the OPCC previously agreed a joint policy for the management of risk, in line with the Cabinet Office approved Management of Risk (M_o_R) approach.

4.8	Risk Grading Criteria

The strategic risk register identifies the key strategic risks to the force. In the main, these risks represent long-term issues and typically remain on the register for long periods.

4.9	All risks are scored on an ascending scale of 1-4 in terms of impact and likelihood. Multiplication of these 2 figures leads to a Risk Score, which is expressed as a Red/Amber/Green or ‘RAG’ rating.

| Impact | Very High | 4 | 8 | 12 | 16 |
| --- | --- | --- | --- | --- | --- |
|  | High | 3 | 6 | 9 | 12 |
|  | Medium | 2 | 4 | 6 | 8 |
|  | Low | 1 | 2 | 3 | 4 |
|  |  | Low | Medium | High | Very High |
|  |  | Probability |  |  |  |

4.10	Risk Control

Once a risk has been analysed and scored, a basic risk strategy is 	determined by the Responsible Officer. The chosen strategy falls into one of 	the following four categories below.

- Treat – Take action to reduce the probability or mitigate the impact of the risk

- Tolerate – Accept the risk and take no further action at this time

- Transfer – Make someone else responsible for the risk, such as through contracting out, a service level agreement, or an insurance policy

- Closed – Withdraw from the activity that is at risk

If the chosen risk strategy is to treat the risk, then consideration is given to the risk controls that already exist and those which would need to be put in place to reduce the probability of the risk occurring or mitigate its impact should it occur.

5 Financial Implications and Budget Provision

  - There are no direct financial implications because of this report. Financial implications because of each risk will be assessed and managed on an individual basis.

- Human Resources Implications

  - Providing professional advice on risk management is the responsibility of the 	Corporate Governance and Business Planning team.

  - General responsibility for managing risk forms an integral part of the job 	descriptions of individuals throughout the Force.

- Equality Implications

  - There are no known equality implications associated with the implementation 	of the Risk Management Policy.

  - Where a particular risk is identified that could have an impact on the Force’s 	equality objectives that risk will be assessed and managed in line with the 	Risk Management Policy.

- Risk Management

  - One of the main aims of the Risk Management Policy is to achieve consistent application of risk management principles and techniques across all areas of the Force and NOPCC.

  - If the Force and NOPCC do not practice effective risk management within their decision making there is a risk of non-compliance with the principles set out in the Joint Code of Corporate Governance.

- Policy Implications and links to the Police and Crime Plan Priorities

  - An understanding and appreciation of strategic risk is important in determining 	the priorities in the Police and Crime Plan, and 	subsequently informing the 	development of effective strategies, policies and plans to address those 	priorities. It is expected that the implementation of the 	Risk Management 	Policy will lead to improved understanding of strategic risk and therefore 	impact positively on the achievement of Police and Crime Plan 	objectives.

- Changes in Legislation or other Legal Considerations

  - Where potential changes in legislation or other legal considerations represent 	a significant threat or opportunity for the Force or the NOPCC these are 	evaluated and managed in line with the Risk Management Policy.

- Details of outcome of consultation

11.1	Each Strategic Risk has been assessed with the relevant risk owner and the DCC and Chief Executive of the NOPCC, respectively.

12. Appendices

12.1	Appendix 1 – Force Strategic Risk Register

Appendix 2 – Mitigation to Force’s Strategic Risk

Appendix 3 – OPCC Corporate Risk Register